## Project Gantt Chart
Project gantt chart
Task ID | Task Name | Planned Duration (days) | Assigned group member(s)
T1 | Complete task delivery form | 14 | Connor Hill
T2 | Complete Gantt Chart | 14 | Connor Hill
T3 | Complete use-case diagram | 14 | Whole group
T4 | Set-up and connect database | 14 | William Blackie, Jake Chapman
T5 | Develop login function | 14 | Connor Hill, Jonas Arud
T6 | Test login function | 14 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 14 | Whole group
T8 | Produce sprint presentation | 14 | Whole group
T9 | Complete task delivery form 2 | 1 | All
T10 | Update Gantt Chart 2 | 14 | All
T11 | Complete functionality Customer | 14 | Connor Hill, Tom Vanlaer-McCanna
T12 | Complete functionality of Driver | 14 | William Blackie, Jake Chapman
T13 | Complete functionality of Admin | 14 | Jonas Arud
T14 | Weekly sprint review | 7 | All
T15 | Complete Sprint presentation | 14 | All
T16 | Test respective module | 14 | All
T17 | Handle session timeout | 7 | William Blackie, Jake Chapman
T18
T19
Colour | Type
Actual
Planned
Task | Planned Start | Planned Duration (days) | Actual Start | Actual Duration (days) | Percent Complete | time axis 2018-10-29 to 2018-12-10
T1 | 2018-10-29 | 14 | 1 | 1 | 100%
T2 | 2018-10-29 | 14 | 1 | 1 | 100%
T3 | 2018-10-29 | 14 | 1 | 1 | 100%
T4 | 2018-10-29 | 14 | 2 | 7 | 100%
T5 | 2018-10-29 | 14 | 2 | 11 | 100%
T6 | 2018-10-29 | 14 | 2 | 13 | 100%
T7 | 2018-11-04 | 7 | 2 | 1 | 100%
T8 | 2018-11-04 | 7 | 2 | 7 | 100%
T9 | 2018-11-12 | 14 | 1 |  | 100%
T10 | 2018-11-12 | 14 | 1 |  | 75%
T11 | 2018-11-12 | 14 | 1
T12 | 2018-11-12 | 14 | 1 |  | 50%
T13 | 2018-11-12 | 14 | 1
T14 | 2018-11-12 | 7 | 2 | 1
T15 | 2018-11-12 | 14 | 2
T16 | 2018-11-12 | 14 | 2
T17 | 2018-11-12 | 7 | 1 | 2 | 100%
T18
T19

## Sheet1
Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s)
T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill
T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill
T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group
T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman
T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud
T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group
T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group