## Project Gantt Chart
Project Gantt Chart
Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s)
T1 | Complete task delivery form | 2 | Connor Hill
T2 | Complete Gantt Chart | 2 | Connor Hill
T3 | Complete use-case diagram | 2 | Whole group
T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman |  |  | Colour | Type
T5 | Develop login function | 2 | Connor Hill, Jonas Arud |  |  |  | Actual
T6 | Test login function | 2 | Tom Vanlaer-McCanna |  |  |  | Planned
T7 | Weekly sprint review | 2 | Whole group
Periods (Weeks)
Task | Planned Start (Period) | Planned Duration (Periods) | Actual Start (Period) | Actual Duration (Periods) | Percent Complete | 1 | 2 | 3 | 4 | 5 | 6
T1 | 1 | 2 | 1 | 1 | 100%
T2 | 1 | 2 | 1 | 1 | 100%
T3 | 1 | 2 | 1 | 1 | 100%
T4 | 1 | 2 | 1 |  | 0%
T5 | 1 | 2 | 1 |  | 0%
T6 | 1 | 2 | 1 |  | 0%
T7 | 1 | 2 | 1 |  | 0%