## Project Gantt Chart
Project gantt chart
Task ID | Task Name | Planned Duration (days) | Assigned group member(s)
T1 | Complete task delivery form | 14 | Connor Hill
T2 | Complete Gantt Chart | 14 | Connor Hill
T3 | Complete use-case diagram | 14 | Whole group
T4 | Set-up and connect database | 14 | William Blackie, Jake Chapman
T5 | Develop login function | 14 | Connor Hill, Jonas Arud
T6 | Test login function | 14 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 14 | Whole group
T8 | Produce sprint presentation | 7 | Whole group
Colour | Type
Actual
Planned
Task | Planned Start | Planned Duration (days) | Actual Start | Actual Duration (days) | Percent Complete | time axis 2018-10-29 to 2018-12-10
T1 | 2018-10-29 | 14 | 1 | 1 | 100%
T2 | 2018-10-29 | 14 | 1 | 1 | 100%
T3 | 2018-10-29 | 14 | 1 | 1 | 100%
T4 | 2018-10-29 | 14 | 2 | 7 | 100%
T5 | 2018-10-29 | 14 | 2 | 11 | 100%
T6 | 2018-10-29 | 14 | 2 | 13 | 100%
T7 | 2018-11-04 | 7 | 2 | 1 | 100%
T8 | 2018-11-04 | 7 | 2 | 7 | 100%

## Sheet1
Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s)
T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill
T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill
T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group
T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman
T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud
T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group
T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group